## Slide 1: Technical Consortium Meeting
November 2014

## Slide 2: Topics:
Cost Sharing (Copay) Updates
Encounter Claims Data Exchange/Blind Spots Updates
APR-DRG Project Updates
ICD10 Project Updates
FQHC/RHC Project Updates
PCP Rate Parity Project Updates
AHCCCS CRN Expansion Project (999 Lines) Updates
Greater AZ SMI Integration Updates
GMH/SA Duals Integration Updates
Encounter Data Audits
TPL Workgroup Updates
Other Updates

## Slide 3: Cost Sharing (Copays)
Previously proposed additions and/or modifications to the current copay populations, services, amounts, etc… for 1/1/2015 are delayed pending feedback from CMS
It is anticipated that this delay will be a minimum of 90 days, but could be longer
AHCCCS will provide reasonable pre-notice of new implementation timeframes as soon as they become available

## Slide 4: Encounter/Claims Data Exchange/Blind Spots
  AHCCCS will manage an ongoing exchange of encounter and claims data to Contractors in order to eliminate “blind spots” for services provided to a member shared by multiple programs (In compliance with Federal privacy regulations); Contractors should use this information to develop short- and long-term strategies to improve care coordination
  Ongoing – provide at least quarterly

## Slide 5: Encounter/Claims Data Exchange/Blind Spots (cont.)
      Planned additions to the Data Exchange include the integration of - Medicare Paid Claims Data (Part D; Medicare FFS) – In progress; D-SNP - Completed
      Quarterly data extracts are based on Claims and Encounters adjudicated within the reporting ¼
      AHCCCS is also evaluating Contractor requested elements including revenue code line level detail information and recipient behavioral health category as supplemental or additional data for the quarterly Data Exchange

## Slide 6: APR-DRG’s
Implemented 10/1/2014 Implementation (based upon Dates of Discharge)
Technical Workgroup meeting materials available at http://www.azahcccs.gov/commercial/EDIresources/EDITechnicalWorkgroups.aspx
3 Key Forms of Project Documentation –
  AHCCCS Policy Document (updated Track Changes version currently posted)
  AHCCCS Rule
  AHCCCS DRG Calculator

## Slide 7: APR-DRG’s (cont.)
Contractor monthly project Milestone Reporting began in February, 2014 and can discontinue at plan implementation
Weekly reporting related to APR-DRG claims processing required on a weekly basis each Friday now through the end of the calendar year

## Slide 8: ICD-10
The AHCCCS ICD10 Project implementation 10/1/2015
Testing with Trading Partners began in January of 2014 and will continue through September of 2015
ICD10 Effective Date - October1 2015 (OP Dates of Services or IP Dates of Discharge)
AHCCCS will be supplying a limited set of required Testing Scenarios that all Contractors must successfully complete prior to implementation (timing TBD)

## Slide 9: ICD-10 (cont.)
  Ongoing Contractor Milestone Reporting and Tracking should continue until 10/1/15
  Post implementation status reporting requirements are current under development

## Slide 10: FQHC/RHC Project
FQHC/RHC Payment Alignment
  Contractor’s will need to pay FQHC/RHC unique PPS rates for each “visit” (separate service not with same
  Ongoing Technical workgroups – material posted to the Technical workgroup webpage http://www.azahcccs.gov/commercial/EDIresources/EDITechnicalWorkgroups.aspx
FQHC/RHC Billing Rules (FFS Billing Manual Chapter) to be released this week
Next Workgroup timing and scope under evaluation

## Slide 11: PCP Rate Parity
AHCCCS will make quarterly cost-settlement payments to the Contractor based upon adjudicated/approved, error free PCP Rate Parity encounter data
Contractors will be required to refund payments to AHCCCS for any reduced claim payments in the event that a provider is subsequently “decertified” for enhanced payments as result of subsequent audits or other changes to providers
A650/A655 Edits changed to external pends for the current cycle

## Slide 12: PCP Rate Parity (cont.)
“Catch-up” cost-settlement report for qualified encounters adjudicated/approved between 8/1/2013 and 12/31/2013 a well as 1/4ly report for the January through June time periods were run and distributed to Contractors; AHCCCS also ran Error Reports out of these processes of those items excluded due to Plan error or Federal claiming concerns
Contractor Error Reports as noted above will be distributed to the plans for correction of included encounters shortly

## Slide 13: AHCCCS CRN Expansion Project (999 Lines)
AHCCCS 999 UB Lines HIPAA compliance changes proposed to begin mid to late 2015 and implement in late 2015 to early 2016
Will fully remediate the PMMIS system to expand the CRN by 1 additional digit for all form types; i.e.… AHCCCS CRN’s will go from 14 digits to 15 digits in length
Will impact and require testing with Contractors and Trading Partners
Detailed timelines in development

## Slide 14: Greater AZ SMI Integration
ADHS/BHS will award two contracts one for southern AZ GSA’s and one for northern AZ GSA’s to serve as an Integrated Contractor (providing both behavioral and physical health services to SMI members) and the RBHA for all other members in these GSA’s
AHCCCS assessment of impacts, required systems changes and timelines in progress

## Slide 15: GMH/SA Duals Integration
AHCCCS will identify Medicare/Medicaid dual eligible General Mental Health (GMH)/Substance Abuse (SA) members and will assign their AHCCCS Health Plan to provide both their behavioral health services
AHCCCS assessment of impacts, required systems changes and timelines in progress

## Slide 16: Encounter Data Audits
AHCCCS OIG has been conducting assessments or inappropriate billing practices based upon processed claims and encounters data
A sample of the first of these audits, inappropriate use of 50 vs. RT and LT modifiers, will be provided for plan validation and response prior to provider contact

## Slide 17: TPL Workgroup Updates
Refer to Webpage
http://www.azahcccs.gov/commercial/EDIresources/EDITechnicalWorkgroups.aspx
AHCCCS staff are currently working with our ISD on identified next steps and agreed upon documentation
Status summary to be sent to Contractors shortly

## Slide 18: Other Updates
Pharmacy NDC related Pends (N020/N027, etc…)
VFC related Pends (Z627, Z628 and Z629)
Other?/Open Discussion

## Slide 19: Questions?

## Slide 20: Thank You.