## RFP-Housing Administrator
PROCUREMENT TIMELINE
YH21-0002 AHCCCS HOUSING ADMINISTRATOR RFP
ACTIVITY / MILESTONE | DATE
Requirements Gathering
RFP Finalized | 2020-10-07
Newspaper Advertising Date | 2020-10-05
RFP Publication Date | 2020-10-08
Written Questions Due Date | 2020-10-21
Develop Answers | 2020-10-29
Solicitation Amendment #1 Issued | 2020-10-30
Solicitation Amendment #2 Issued | 2020-11-06
Evaluator Training | 2020-10-19
Deadline to request access to SFTP server | November 4, 2020 - Amended (Amd #2) to November 12, 2020
Proposal Due Date | 2020-11-19
Procurement Review | November 20 - December 2, 2020
Independent Evaluator Scoring | November 20 - December 2, 2020
Consensus Scoring (Evaluation meetings) | Decmeber 3 - 7, 2020
Clarifications | December 21, 2020 - January 6, 2021
Bafo Negotiations | 1/11/2021 - 1/15/2021
Best and Final Offers Due | 2021-01-22
Final Evaluation Meeting | 2021-01-20
Award Recommendation to Chief Procurement Officer | 2021-01-12
Official Award Date | 2021-01-25
Contract Effective Date/Start of Services | 2021-10-01
Transition Period (if needed) | February - September 2021
To insert into RFP:
RFP Release | Ocober 7, 2020
Pre-Proposal Conference | N/A
Offeror Questions Due | 2020-10-21
Deadline to request access to SFTP server | 2020-11-04
Offeror’s Proposals Due | 2020-11-19
Final RFP Award (Subject to change) | 2021-01-01
Services Start Date | October 1, 2021* *Unless otherwise changed in writing by AHCCCS